## Sheet1
			All metal print heads schedule – Product Development Cycle
			03-02	03-09	03-16	03-23	03-30	04-06	04-13	04-20	04-27	05-04

TASKS		OWNER	EVT / Engineering Verification Test			DVT/SAT – Qualification / Design Verification/Ship Approval Test				Production & Inventory Buildup
R&D – Mechanical
Define dual specifications		Seth / Brent
Redesign of plastic		Brent
Design machined parts		Seth / Brent
Build Flexys to test (Mini and TAZ)		Brent
Make drawings for machined parts		Seth
BOM for Flexy (Mini)		Seth
BOM for Flexy (TAZ)		Seth
BOM for Dual		Seth
BOM for DualFlexy		Seth
R&D Electrical
Define input requirements		Brent
Decide what machines will be supported		Seth/Steven
Design harnesses		Brent
Firmware		Brent / Patrick
Software
Cura profiles		Brent / Patrick
Any needed Cura changes		Brent / Steven
Build & Test
Test Flexys		Brent
Build up proto Dual		Brent / Patrick
Build up final Dual		Brent / Patrick
Build up final DualFlexys		Brent / Patrick
Build up final Flexys (Mini)		Brent / Patrick
Build up final Flexys (TAZ)		Brent / Patrick
Have “user” go through installation
Test Flexy on glass		Brent
Packaging / Documentation
Design packaging		Seth/Brent
Installation OHAI		Patrick
Procurement
Camellia (DVT/SAT) Parts
Production Parts – Long lead
Inventory Hex Nozzles		Patrick
Choose build qty		Seth/Steven
DVT/SAT Parts		Toni
Production Parts		Toni
Plastic		Seth/Stan
Manufacturing
Process step define (presub-FA)			1st pass
Process step layout
Assembly line layout & BOM
Mfg line 2 construction/ purchase
Resource Plan proposal/ approval
Recruiting mfg staffs
Training new team
Build production		Chris
Assembly OHAI Kits		Chris
PreSub Op setup & production prep
Cycle time modeling			1st pass
Presub/Sub Test Defined
Pre/Sub Test Equip Des/Setup
- Harness Test Fixture
- Other fixtures
MO		Chris
Marketing / PR / Sales / CS
Final Product Photos		Harris
Product Pages		Harris
Customer support training
Product Description		Harris