## Sheet1
HALIBUT Extruder Program Schedule – 6 Month Product Development Cycle
Wk1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24
6 weeks					4 weeks				5 weeks					6 weeks					3 weeks
Technology / Staging					Feasibility				EVT – Eng Verification Test					DVT / DMT - Design Verification/ Maturity					SAT–Ship Apprv			Production/ Ramp
R&D Enabling technologies					Demo Tech & Financial Feasibility / - Can we productize it? / - Is it worth the investment?				Design Validation / (Functionally focused)					Reliability & Maturity focused					Manufacturability Quality / Shippability / Focused			Build up Inventory & Ramp

- Build sub-assembly prototypes					- Build system prototype (1-2)				- Build 5-10 prototypes					- Build 10-20 final config machines					- Build 20-50 by MFG
- Verify early design concepts					- Test & DEMO 'core'				- Test, validate designs, modify/					- Reliability test
- Use “mule” platform					functionality				Re-validate					. Long term reliability					- Finalize MR/DR Process
- Prepare for Feasibility 'early'					- Finalize MR/DR Process				- Demo all intended all functionality					. Shock/ Vib					- Long term reliability
Prototypes – order parts, etc …					- Prepare EVT BOM, risk order				- Performance testing					. Environmental					testing					- Prepare EVT BOM. risk order
					- Finalize design configuration					. EMI
					- Prepare FIN projection				- Finalize DVT SW/FW					…
					. Cost – COGS					- Performance testing
- Prepare MR (Marketing Requirement)					. 3Y Sales/ Revenue, Income				- Prepare DVT BOM, risk order					- Materials testing
- Prepare MR Response ~ DR (Design Reqmt)					. ROI, …				- DFM, DFR review					- Safety
					(Design for Manufacturability, Reliability)					- Userability
					- Design Review					- Prepare Final/Production BOM, order
- Prepare report/presentation to get					- Prepare report/presentation to				- Prepare report/presentation to get					- Prepare report/presentation to get approval to
Approval to enter Feasibility Phase					Get approval to enter EVT				approval to enter DVT					enter SAT

		date				date				date					date					date
		MR		date		Order/build prototypes				EVT build commences					DVT build commences					SAT build commences
				DR
					date				date					date
					date		Test				EVT test					DVT					SAT Test
					Order			date			date
				Parts for FEA				Finalize MR/DR			DFM/ DFR review

					date
					Design locked

					date					date
					DVT SW Rel					SAT SW Rel

					date					date					date
					EVT BOM					DVT BOM					SAT/Prod BOM

					date					date					date
					Order	EVT				Order	EVT					Risk Order SAT

					date				date					date					date			date
				R&D Exit		FEA Entry				EVT Entry			EVT Exit		DVT Entry				DVT Exit		SAT Entry		SA	Review

Key Enabling Technologies					Items to Validate:					Items to Verify:
					1)	Extrudability				1) Performance(speed,...)
1)					2)	Repeatability				2) Repeatability/Reliability
2)					3)	Userablity				3) Userability
3)					4)	Mechanical Spec				4) Environmental
					5)	Electrical spec				5) Op Shock/ Vibration
					6) Non-Opshock
					7) EMC/FCC
					Type of Test					Type of Test
					1)					1) Extrude
					2)
					3)					3) Early customer usage/feedback
					4)					4) Hot, Hot/wet, Cold
					5)					5) Bump Test/ Vibration table
					6) Drop test/ FedEx test
					7) Near/far field test & FCC
					Test Acceptance or P/F Criteria
					1)
					2)					Test Acceptance or Pass/Fail Criteria
					3)					1)
					4)					2)
					5)					3)
					4)
					5)

Rules:					Design changes allowed - No architect-related changes after config “locked” date unless program risks such as schedule, cost, … are studied & approved by the PAC					Minor changes/ improvements learned via RBF cycles allowed. No config/architect related changes w/o PAC approved					“Ship” config hence NO change unless last minute discovery from SAT test bed renders product un-shippable, need PAC approval

PAC
Signed Off