## Sheet1
Easy TAZ Mini - Work Breakdown Schedule
TASKS		OWNER	MAN Hrs	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22
				EVT					DVT					SAT					Production
Architect		Seth
Cube or Lulzbot? Decision		Seth
- CAD		Seth
- Build mockups		Seth
- Cost estimate		Seth/ Chris
Electronics- Controller & Comm		TBD
- Research features		Aaron
- Research Market trends		Aaron
- Pros & Cons on FW effort		Aaron
- Final Config/feature proposal		Seth
- Final Config Decision		All
Non-UL/UL Ready/ Full UL?		Seth & All
- Define what need to be done		Seth/ Chris
- Re cost estimate		Seth
Software
SW Feature List		Seth/ Aaron
BBB – LCD touch		Aaron/Aeva
BBB – WiFi		Aaron/Aeva
BBB – Smart Phone		Aaron/Aeva					no longer applied
BBB – USB		Aaron/Aeva					USB stick only
BBB – Camera		Aaron/Aeva
User Interf Menu Diagr/Coding		Aaron/Aeva
Interface Controls (Touch Scrn)		Aaron/Aeva
System Integration		Aaron/Aeva
Firmware
RAMBO – SD		Aaron/Seth					no longer applied
RAMBO – BBB		Aaron/Seth
RAMBO – EZT HW		Aaron/Seth
Auto Leveling		Aaron/Seth
Mechanical		Seth
Frame		Seth
X-Axis		Seth
Y-Axis		Seth
Z-Axis		Seth
Extruder		Seth/ Brent
Drive System		Seth
New Spool loc/feed		Seth
Motor Selection		Seth
Nozzle Sel/ Design		Seth/ Brent
Heat bed		Seth/ Brent
- PET tape?
- Holding the bed?
Auto Bed Leveling		Seth/ Brent
Electronics/ Electrical		Seth
Wiring (HW vs Conn)		Seth/ Chris
Power Supply		Seth/ Chris
Lights/LEDs		Seth
Grd/ EMI Shielding		Seth/ Chris
Camera		Seth
LCD		Seth/ Aaron
SD or USB		Seth & All
Switches		Seth
Breadboard Testing		Seth/ Chris

TASKS		OWNER	MAN Hrs	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22
				EVT					DVT					SAT					Production
Build & Test		Seth
Build Prototypes/ Test machines		Seth/ Chris					Guava!
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Chris
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth/ Chris
Long Term Reliability		Seth/ Brent
Packaging/ Documentation		Steven
Shipping Foam
Unbox Manual
Operation Manual
Print Profiles
BOM Creation		Seth
Procurement		Seth/ Chris
DVT Parts		Seth
SAT		Seth
Production		Seth/ Chris
Risk Purchases Long Lead Items		Seth/ Chris
Plastic		Chris/ Stan					07-14	30 SAT build			08-11	200 production
Manufacturing		Chris
Build SAT machines
Assembly OHAI Kits		Chris/Robert
Assembly line Layout		Chris
PreSubs		Chris
Cycle time modeling		Chris
Cycle time verification		Chris
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris
Pre/Sub Test Equip Des/Setup		Chris
OpenERP Routing		Chris
Resource Plan		Chris
Marketing & Communications		Harris
SEO Optimization		Harris/Steven					Define terms
Product Photo		Harris/Emily					Feat.				Feat.				Feat.	Product
Feature Promotion		Harris/Emily					Insta.				Pin.				Reddit				Forum				All
Product Review (x 4)		Harris					Identify/Negotiate					Confirm				Ship	In Review					Back
Sales and Support Call Scripts		Rachael/Jason					Draft					Done
Product Video		Harris/Emily					Shots	Log.	Film and Edit					Post
Product Flyer		Harris/Steven					Layout			Order
Price Decision		Jeff/Greg					Final
Sales Sheet and Leads		Harris/Rachael					Draft			Done
Reseller Listing and Leads		Harris/Rachael					Draft			Done					Send
Website Listing		Harris/Steven					Draft			Done					Post
Press Release		Harris					Draft			Done					Send
Print Sample of Build Area (x 5)		Brent
Co-Brand (SparkFun/OSHWA)		All
Go-Live		Harris/Steven
Certifications		All
Promotion via Sponsorship		Harris/Steven