## Sheet1
			LulzBot Mini – Product Development Cycle – v4.0
			08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15	12-22	12-29	01-05	01-12	01-19
								CES	SA
TASKS		OWNER	EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia / Daffodil)					Production & Inventory Buildup / (Daffodil)
R&D – Mechanical		Seth
Drive rod Wobble		Seth
Hex Nozzles breaking		Brent
Install new nozzles on all C&C printers		Bernt
Fuzzies on Wiper		Brent

R&D Electrical		Seth
ESC Testing		ChrisW
Order parts once testing is complete		Seth
Test new Mini-Rambo when it arrives		ChrisW

Software		Steven
Bug testing		Steven						Release
GUI changes		Steven
Print Profiles		Brent/Steven						Done
Packaging		Steven

Code Release		Steven						DVT/SAT
Build & Test		Seth
Test Plan		Seth/ Chris
Build Prototypes/ Test machines		Seth/ Brent
Functional		Seth/ Brent
Speed		Seth/ Brent						Done
Mechanical Performance		Seth/ Brent
Usability		Seth/ Steven
Environmental		Seth/ Brent						Done
Op-Shock		Seth/ Brent						Done
Non-Opshock		Seth/ Brent						Done
EMC		Seth
Long Term Reliability		Seth/ Stan
Packaging / Documentation		Steven
Machine for foam prototype		Seth
Shipping Foam		Steven						Done
Final Foam design verify		Steven						Done
Internal Drop Test								Done
Fed-EX Test		Steven						Done
Boxes								Done
USB
Operation Manual		Steven
- Quick Start Guide		Steven						Print
Web site pages
Consumer's Open Box Exp Test		Steven
Packing list		Seth						Print
Quality Assurance Record		Seth						Print
Poster		Steven						Print
CE Declaration of Conformity								Print
Safety guide		Steven						Print
Procurement
Camellia (DVT/SAT) Parts		Seth/ Toni						Done
Production Parts – Long lead		Seth/ Jeff
Production Parts		Toni/Seth						sheet metal, PEI
Plastic		Chris/ Stan						Extended
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris	1st pass
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build DVT/SAT machines		Chris						Crotons	Done
Assembly OHAI Kits		Seth/Robert
PreSub Op setup & production prep		Chris
Cycle time modeling		Chris	1st pass
Cycle time verification/ Opti		Chris						Extended					20prt/day
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris						Done
Pre/Sub Test Equip Des/Setup		Chris
- Harness Test Fixture		Brent
- Other fixtures
MO		Chris						Croutons
Marketing / PR		Harris
Frame Design		Kevin/Natasha						Done
Customer Survey		Natasha/Harris						Done
Market Research Review		Harris						Done
Product Packaging		Kevin/Natasha						Done
Teaser / Promotional Item		Marketing (All)						Done
Press Engagement		Harris/Schwartz
LulzBot.com/Mini Landing Pg.		Marketing (All)
LulzBot.com/Rocktopus Landing Pg.		Marketing (All)
Reseller Engagement		Rachael/Ben
Product Collateral Design		Kevin/Claudio
CES Launch Prep		Marketing (All)
CES Follow Up
Final Product Photos		Kevin
Product Description		Harris/Natasha